## Project Planner
Online Exam Face Detection Gantt Chart
by HummingBird Sdn. Bhd. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Project Initiation
1.1 Assign project manager | 1 | 1 | 1 | 1 | 100%
1.2 Develop project charter | 1 | 3 | 1 | 2 | 100%
1.3 Identify stakeholders | 2 | 4 | 2 | 3 | 100%
1.4 Identify project guideliness | 2 | 5 | 2 | 5 | 100%
2. Project Planning
2.1 Prepare scope statement | 7 | 4 | 6 | 4 | 100%
2.2 Create WBS | 7 | 1 | 6 | 1 | 100%
2.3 Plan cost management | 8 | 5 | 7 | 6 | 5%
2.4 Plan risk management | 8 | 4 | 7 | 5 | 5%
2.5 Plan communication management | 9 | 3 | 9 | 4 | 15%
3. Project Execution
3.1 Direct and manage project work | 7 | 31 | 7 | 29 | 0%
3.2 Develop and manage project team | 12 | 31 | 10 | 29 | 0%
3.3 Manage communications | 12 | 31 | 12 | 29 | 0%
3.4 Manage stakeholder engagement | 15 | 31 | 13 | 29 | 0%
4. Project Monitoring & Controlling
4.1 Monitor and control project work | 7 | 20 | 7 | 21 | 0%
4.2 Control scope | 16 | 20 | 17 | 21 | 0%
4.3 Validate scope | 19 | 20 | 20 | 21 | 0%
4.5 Control quality | 16 | 20 | 16 | 23 | 0%
4.6 Control communication | 14 | 20 | 13 | 21 | 0%
4.7 Control risk | 17 | 20 | 17 | 23 | 0%
4.8 Control costs | 17 | 20 | 16 | 23 | 0%
4.9 Progress reports | 20 | 18 | 19 | 18 | 0%
5. Project Closing
5.1 Finalize project | 39 | 2 | 42 | 2 | 0%
5.2 Prepare project report | 40 | 2 | 43 | 4 | 0%