## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Online Exam Face Detection (OeFD)
PROJECT MANAGER | Nurul Aishah binti Mohd Zaini
TEAM MEMBERS | 1. Nurul 'Izzah binti Muhammad Zawave 2. Thanushaini A/P Poobalan 3. Siti Kamariah binti Ismail
COMPANY NAME | HummingBird Sdn. Bhd.
DATE | 2021-11-02 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Create Project Charter | Aishah | 2021-10-13 | 2021-10-15 | 2 | 100%
1.1.1 | Assign Project Manager | All | 2021-10-16 | 2021-10-17 | 1 | 100%
1.1.2 | Revision of Project Charter | Kama | 2021-10-18 | 2021-10-19 | 1 | 100%
1.2 | Research | Thanu | 2021-10-20 | 2021-10-25 | 5 | 99%
1.2.1 | Gather Materials | Aishah | 2021-10-26 | 2021-10-31 | 5 | 100%
1.2.1.1 | Identify Softwae and Hardware | Izzah | 2021-11-01 | 2021-11-04 | 3 | 98%
1.2.1.2 | Identify Programming Language | Izzah | 2021-11-05 | 2021-11-06 | 1 | 100%
1.2.1.3 | Gather Research Papers and Datasets | Thanu | 2021-11-07 | 2021-11-09 | 2 | 85%
1.2.1.4 | Review Research Materials | Kama | 2021-11-10 | 2021-11-11 | 1 | 85%
1.3 | Projections | Aishah | 2021-11-12 | 2021-11-13 | 1 | 80%
1.4 | Stakeholders | Thanu | 2021-11-14 | 2021-11-17 | 2 | 98%
1.4.1 | Identify Stakeholders | Izzah | 2021-11-14 | 2021-11-17 | 2 | 100%
1.4.2 | Identify Target Users | Kama | 2021-11-14 | 2021-11-17 | 2 | 100%
1.5 | Guidelines | Izzah | 2021-11-18 | 2021-11-19 | 1 | 89%
1.5.1 | Indentify Project Guidelines | Aishah | 2021-11-18 | 2021-11-19 | 1 | 89%
1.6 | Project Initiation | Izzah | 2021-11-19 | 2021-11-19 | 1 | 100%
2 | Project Definition & Planning
2.1 | Requirements Collection | Aishah | 2021-11-20 | 2021-11-24 | 4 | 95%
2.1.1 | Identify Functional & Non-Functional Requirements | Kama | 2021-11-25 | 2021-11-27 | 2 | 98%
2.1.2 | Interviews | Thanu | 2021-11-28 | 2021-11-29 | 1 | 90%
2.1.2.1 | Interview Students | Izzah | 2021-11-30 | 2021-12-01 | 1 | 90%
2.1.3 | Observations | Thanu | 2021-12-02 | 2021-12-04 | 2 | 85%
2.1.3.1 | Observe Students During Online Exam | Kama | 2021-12-05 | 2021-12-06 | 1 | 95%
2.1.3 | Group Decision Making | Aishah | 2021-12-07 | 2021-12-08 | 1 | 100%
2.1.3.1 | Indentify Modules | Izzah | 2021-12-09 | 2021-12-12 | 3 | 100%
2.2 | Scope and Goal Setting | Kama | 2021-12-13 | 2021-12-15 | 2 | 98%
2.2.3 | Product Analysis | Izzah | 2021-12-16 | 2021-12-17 | 1 | 95%
2.2.3.1 | Identify Current Product | Thanu | 2021-12-18 | 2021-12-21 | 3 | 100%
2.2.3.2 | Identify Proposed Product | Aishah | 2021-12-22 | 2021-12-25 | 3 | 99%
2.2.3.3 | Identify Product Architecture | Kama | 2021-12-22 | 2021-12-25 | 3 | 95%
2.2.4 | Identify Alternatives | Thanu | 2021-12-26 | 2021-12-29 | 3 | 96%
2.3 | Budget | Kama | 2021-12-30 | 2021-12-31 | 1 | 85%
2.3.1 | Cost Estimation | Izzah | 2022-01-01 | 2022-01-02 | 2 | 85%
2.4 | Create WBS | Aishah | 2022-01-03 | 2022-01-04 | 1 | 95%
2.4.1 | Decomposition | Kama | 2022-01-05 | 2022-01-06 | 1 | 95%
2.4.2 | Module & Task Distribution | Izzah | 2022-01-05 | 2022-01-06 | 1 | 100%
2.5 | Extablish Scope | Thanu | 2022-01-06 | 2022-01-07 | 1 | 100%
2.5.1 | Scope Inspection | Aishah | 2022-01-07 | 2022-01-08 | 1 | 95%
2.6 | Control Scope | Kama | 2022-01-09 | 2022-01-10 | 1 | 95%
2.6.1 | Variance Analysis on Scope | Thanu | 2022-01-10 | 2022-01-12 | 2 | 90%
2.7 | Risk Management Plan | Izzah | 2022-01-12 | 2022-01-14 | 2 | 98%
2.7.1 | Identify Possible Risks | Kama | 2022-01-14 | 2022-01-15 | 2 | 100%
3 | Project Launch and Execution
3.1 | Status and Tracking | Aishah | 2022-01-17 | 2022-01-20 | 3 | 0%
3.2 | KPIs | Izzah | 2022-01-20 | 2022-01-24 | 4 | 0%
3.3 | Monitoring | Aishah | 2022-01-25 | 2022-02-04 | 7 | 0%
3.3.1 | Project Assissting | Aishah | 2022-02-04 | 2022-02-09 | 5 | 0%
3.4 | Project Process Updates | Kama | 2022-02-10 | 2022-02-10 | 1 | 0%
3.5 | Documentation | Thanu | 2022-03-03 | 2022-03-06 | 3 | 0%
3.5.1 | List Project Progress | Izzah | 2022-03-06 | 2022-03-07 | 1 | 0%
3.5.2 | Final Report | All | 2022-03-08 | 2022-03-10 | 2 | 0%
4 | Project Performance and Monitoring
4.1 | Project Objectives | Thanu | 2022-03-11 | 2022-03-13 | 2 | 0%
4.1.2 | Review Back Objectives and Business Requirements | All | 2022-03-13 | 2022-03-15 | 2 | 0%
4.2 | Quality Deliverables | Kama | 2022-03-15 | 2022-03-18 | 3 | 0%
4.2.3 | Check & Validate Each Module | All | 2022-03-18 | 2022-03-20 | 2 | 0%
4.3 | Module Testing | Aishah | 2022-03-20 | 2022-03-24 | 4 | 0%
4.3.1 | Integrate Modules | Izzah | 2022-03-24 | 2022-03-29 | 5 | 0%
4.3.2 | Run & Validate System | Kama | 2022-04-01 | 2022-04-05 | 4 | 0%
4.3.3 | Indentify Errors | Thanu | 2022-04-01 | 2022-04-05 | 4 | 0%
4.3.4 | Fix Errors | Aishah | 2022-04-05 | 2022-04-10 | 5 | 0%
4.4 | Complete Project Testing | All | 2022-04-11 | 2022-04-16 | 5 | 0%
4.5 | Project Performance | Izzah | 2022-04-16 | 2022-04-20 | 4 | 0%
4.5.1 | Final Report Submition | Thanu | 2022-04-21 | 25/42022 | 3 | 0%
4.5.2 | Project Presentation | All | 2022-04-30 | 2022-04-30 | 1 | 0%