## HummingBird Sdn Bhd
PROJECT TITLE | Online Exam Face Detection (OeFD)
PROJECT MANAGER | Nurul Aishah Binti Mohd Zaini
GROUP NAME | 1) Nurul 'Izzah Binti Muhammad Zawave 2) Siti Kamariah Binti Ismail 3) Thanushaini A/P Poobalan
COMPANY NAME | HummingBird Sdn. Bhd.
DATE | 8th October 2021
GITHUB | https://github.com/HummingBird39/Online-Exam-Face-Detection-OeFD-

## Development
Software Development Estimate
| Productivity factor = 3.13 |  | Penalty Factor: 1.072
1. Labor Estimate | #Hrs/Week | Cost/Unit/Hr. | Subtotals | Calculations
Contractor labor estimate | 4270 | 85.5 | 365085 | 4270*85.5
Project team member estimate | 4880 | 55.5 | 270840 | 4880 * 55.5
Total labor estimate |  |  | 635925 | Sum above two values
2. Function point estimate** | Quantity | Conversion Factor | Function Points | Calculations
External inputs | 8 | 4 | 32 | 8 * 4
External interface files | 4 | 7 | 28 | 4*7
External outputs | 3 | 5 | 15 | 3*5
External queries | 4 | 4 | 16 | 4*4
Logical internal tables | 5 | 10 | 50 | 5*10
Total function points |  |  | 141 | Sum above function point values
Java 2 language equivalency value |  |  | 56 | Assumed value from reference
Source lines of code (SLOC) estimate |  |  | 7896 | 141 * 56
Productivity*KSLOC^Penalty (in months) |  |  | 29.2791 | 3.13 * 8.05 ^1.072 (see reference)
Total labor hours (160 hours/month) |  |  | 4684.6538 | 29.28 * 160
Cost/labor hour (RM120/hour) |  |  | 120 | Assumed value from budget expert
Total function point estimate |  |  | 562158.459 | 4684.65 * 120

## Cost
Project Cost Estimate
| # Units/Hrs | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | RM 273800 | 4.79%
Project Manager | 330 | 80 | 26400
Project team members | 1700 | 65 | 110500
Contractors (10% of software development and testing) |  |  | 136900
2. Hardware |  |  |  | RM 12800 | 0.0022%
2.1 Handled devices | 8 | 600 | 4800
2.2 Serves | 4 | 2000 | 8000
3. Software |  |  |  | RM 501600 | 8.77%
3.1 Licensed software | 8 | 200 | 1600
3.2 Software development* |  |  | 500000
4. Testing (10% of total hardware and software costs) |  |  | 51440 | RM 51440 | 0.1%
5. Training and Support |  |  |  | RM 164500
Trainee cost | 100 | 500 | 50000
Travel cost | 8 | 500 | 4000
Project team members | 1700 | 65 | 110500
6. Reserves (20% of total estimate) |  |  | 200828 | RM 200828 | 3.51%
Total project cost estimate |  |  |  | RM 5719371