## TIME MNGMT CHART HUMMINGBIRD
TIME MANAGEMENT GANTT CHART TEMPLATE FOR ONLINE EXAM FACE DETECTION PROJECT
HummingBird Sdn. Bhd
[ Online Exam Face Detection ]
TASK NAME | START DATE | END DATE | DURATION (days)
Create Project Charter | 2021-10-13 | 2021-10-15 | 3
Assign Project Manager | 2021-10-16 | 2021-10-17 | 2
Revision of Project Charter | 2021-10-18 | 2021-10-19 | 2
Research | 2021-10-20 | 2021-10-25 | 6
Gather Materials | 2021-10-26 | 2021-10-31 | 6
Identify Softwae and Hardware | 2021-11-01 | 2021-11-04 | 4
Identify Programming Language | 2021-11-05 | 2021-11-06 | 2
Gather Research Papers and Datasets | 2021-11-07 | 2021-11-09 | 3
Review Research Materials | 2021-11-10 | 2021-11-11 | 2
Projections | 2021-11-12 | 2021-11-13 | 2
Stakeholders | 2021-11-14 | 2021-11-17 | 4
Identify Stakeholders | 2021-11-14 | 2021-11-17 | 4
Identify Target Users | 2021-11-14 | 2021-11-17 | 4
Guidelines | 2021-11-18 | 2021-11-19 | 2
Indentify Project Guidelines | 2021-11-18 | 2021-11-19 | 2
Project Initiation | 2021-11-19 | 2021-11-19 | 1
Requirements Collection | 2021-11-20 | 2021-11-24 | 5
Identify Functional & Non-Functional Requirements | 2021-11-25 | 2021-11-27 | 3
Interviews | 2021-11-28 | 2021-11-29 | 2
Interview Students | 2021-11-30 | 2021-12-01 | 2
Observations | 2021-12-02 | 2021-12-04 | 3
Observe Students During Online Exam | 2021-12-05 | 2021-12-06 | 2
Group Decision Making | 2021-12-07 | 2021-12-08 | 2
Indentify Modules | 2021-12-09 | 2021-12-12 | 4
Scope and Goal Setting | 2021-12-13 | 2021-12-15 | 3
Product Analysis | 2021-12-16 | 2021-12-17 | 2
Identify Current Product | 2021-12-18 | 2021-12-21 | 4
Identify Proposed Product | 2021-12-22 | 2021-12-25 | 4
Identify Product Architecture | 2021-12-22 | 2021-12-25 | 4
Identify Alternatives | 2021-12-26 | 2021-12-29 | 4
Budget | 2021-12-30 | 2021-12-31 | 2
Cost Estimation | 2022-01-01 | 2022-01-02 | 2
Create WBS | 2022-01-03 | 2022-01-04 | 2
Decomposition | 2022-01-05 | 2022-01-06 | 2
Module & Task Distribution | 2022-01-05 | 2022-01-06 | 2
Extablish Scope | 2022-01-06 | 2022-01-07 | 2
Scope Inspection | 2022-01-07 | 2022-01-08 | 2
Control Scope | 2022-01-09 | 2022-01-10 | 2
Variance Analysis on Scope | 2022-01-10 | 2022-01-12 | 3
Risk Management Plan | 2022-01-12 | 2022-01-14 | 3
Identify Possible Risks | 2022-01-14 | 2022-01-15 | 2
Status and Tracking | 2022-01-17 | 2022-01-20 | 4
KPIs | 2022-01-20 | 2022-01-24 | 5
Monitoring | 2022-01-25 | 2022-02-04 | 11
Project Assissting | 2022-02-04 | 2022-02-09 | 6
Project Process Updates | 2022-02-10 | 2022-02-10 | 1
Documentation | 2022-03-03 | 2022-03-06 | 4
List Project Progress | 2022-03-06 | 2022-03-07 | 2
Final Report | 2022-03-08 | 2022-03-10 | 3
Project Objectives | 2022-03-11 | 2022-03-13 | 3
Review Back Objectives and Business Requirements | 2022-03-13 | 2022-03-15 | 3
Quality Deliverables | 2022-03-15 | 2022-03-18 | 4
Check & Validate Each Module | 2022-03-18 | 2022-03-20 | 3
Module Testing | 2022-03-20 | 2022-03-24 | 5
Integrate Modules | 2022-03-24 | 2022-03-29 | 6
Run & Validate System | 2022-04-01 | 2022-04-05 | 5
Indentify Errors | 2022-04-01 | 2022-04-05 | 5
Fix Errors | 2022-04-05 | 2022-04-10 | 6
Complete Project Testing | 2022-04-11 | 2022-04-16 | 6
Project Performance | 2022-04-16 | 2022-04-20 | 5
Final Report Submition | 2022-04-21 | 2022-04-25 | 5
Project Presentation | 2022-04-30 | 2022-04-30 | 3
MILESTONE 1:
13/10/2021
PROJECT CONCEPT & INITIATION
MILESTONE 2:
20/11/21
PROJECT DEFINITION & PLANNING
MILESTONE 3:
17/01/22
PROJECT LAUNCH & EXECUTION
MILESTONE 5:
21/04/22
PROJECT CLOSING
MILESTONE 4:
11/03/22
PROJECT PERFORMANCE & MONITORING